## Gantt Chart
GANTT CHART
PROJECT TITLE |  | Improved Salmon and Trout Egg Counter |  |  |  | COMPANY NAME | [6 empty] | Pacific Roe Technologies dba Jensorter
PROJECT MANAGER |  | Curtis Edmonson & John Lipor |  |  |  | DATE | [6 empty] | 2022-01-30
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | PCT OF TASK COMPLETE | JANUARY | [19 empty] | FEBRUARY | [19 empty] | MARCH | [19 empty] | APRIL | [19 empty] | MAY | [19 empty] | JUNE
[6 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20 |  |  |  |  | WEEK 21 |  |  |  |  | WEEK 22
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Capstone Initiation
1.1 | Initial Sponsor Meeting ' | Team | 2021-12-03 | 2021-12-03 | 100% | bar: WEEK 8 F
1.2 | One-Minute Summary | Team | 2022-01-03 | 2022-01-07 | 100% | bar: WEEK 1 F; WEEK 8 F
1.3 | Class Check-Ins | Team | 2022-01-07 | 2022-06-03 | 20% | bar: WEEK 1 F; WEEK 5 F to WEEK 6 F; WEEK 8 F; WEEK 9 F; WEEK 13 F; WEEK 17 F; WEEK 21 F
1.6 | Project Proposal | Team | 2022-01-23 | 2022-02-04 | 60% | bar: WEEK 4 M to WEEK 6 F; WEEK 8 F
2 | Research and Design
2.1 | Raspberry Pi/ User Interface | Sydney | 2022-01-23 | 2022-02-18 | 25% | bar: WEEK 4 M to WEEK 7 M; WEEK 8 F
2.2 | Micrcontroler Research | Agustin | 2022-01-23 | 2022-02-18 | 25% | bar: WEEK 4 M to WEEK 7 M; WEEK 8 F
2.3 | Power Rail Research/Design | Trueman | 2022-01-23 | 2022-02-18 | 25% | bar: WEEK 4 M to WEEK 7 M; WEEK 8 F
2.6 | ESP 32 Camera Sensor Design | Sean | 2022-01-23 | 2022-02-18 | 25% | bar: WEEK 4 M to WEEK 7 M; WEEK 8 F
2.4 | Intial Schematic Design (LTSpice) | Agustin/Sean | 2022-01-30 | 2022-02-25 | 0% | bar: WEEK 4 M to WEEK 8 F
2.5 | Counter Sensor Research/Design | Sydney/Trueman | 2022-01-30 | 2022-02-25 | 0% | bar: WEEK 4 M to WEEK 8 F
2.7 | First Chassis Design | Sydney | 2022-01-30 | 2022-03-14 | 0% | bar: WEEK 4 M to WEEK 11 M
2.8 | First Eagle Schematic Design | Sydney/ Agustin | 2022-02-25 | 2022-03-14 | 0% | bar: WEEK 8 F to WEEK 10 R
2.9 | First PCB Design | Sydney/Agustin | 2022-03-11 | 2022-03-18 | 0% | bar: WEEK 8 F; WEEK 10 F to WEEK 11 F
3 | Prototype Build and Testing
3.2 | First Chassis Build | Team | 2022-03-14 | 2022-03-28 | 0% | bar: WEEK 8 F; WEEK 11 M to WEEK 13 M
3.1 | First PCB Build | Team | 2022-03-18 | 2022-04-01 | 0% | bar: WEEK 8 F; WEEK 11 F to WEEK 13 F
3.3 | First Prototype Spin | Team | 2022-04-04 | 2022-04-15 | 0% | bar: WEEK 8 F; WEEK 14 M to WEEK 15 F
3.4 | Prototype Test | Team | 2022-04-15 | 2022-04-18 | 0% | bar: WEEK 8 F; WEEK 15 F to WEEK 16 M
4 | Final Product Build and Testing
3.1 | Prototype Revision | Team | 2022-04-18 | 2022-04-25 | 0% | bar: WEEK 8 F; WEEK 16 M to WEEK 17 M
3.2 | Second Protoype Spin | Team | 2022-04-25 | 2022-04-29 | 0% | bar: WEEK 8 F; WEEK 17 M to WEEK 17 F
3.3.1 | Bonneville Dam Testing | Team | 2022-04-30 | 2022-05-15 | 0% | bar: WEEK 8 F; WEEK 17 F to WEEK 18 F
5 | Capstone Completion
5.1 | Create Final Poster | Team | 2022-05-16 | 2022-06-03 | 0% | bar: WEEK 8 F; WEEK 19 M to WEEK 21 F
5.4 | Final Poster Presentation | Team | 2022-06-03 | 2022-06-03 | 0% | bar: WEEK 8 F; WEEK 21 F
5.2 | Final User Manual/Video | Trueman | 2022-05-23 | 2022-06-10 | 0% | bar: WEEK 8 F; WEEK 20 M to WEEK 22 F
5.3 | Final Report | Team | 2022-05-23 | 2022-06-10 | 0% | bar: WEEK 8 F; WEEK 20 M to WEEK 22 F
5.5 | Sponsor and Advisor Presentation | Team | 2022-06-10 | 2022-06-10 | 0% | bar: WEEK 8 F; WEEK 22 F